## Sheet1
Tasks | Sprint-0 | Sprint-1 | Sprint-2 | Sprint-3 | Hours
Learning ElectronJS | 0.5 | 0 | 0 | 0 | 2
UI Building | 8 | 0 | 0 | 0 | 22
UI Testing & Documentation | 0 | 0 | 0 | 0 | 5
DOM Tree Building | 0 | 0 | 0 | 0 | 24
Integration Tests and Documentaions | 0 | 0 | 0 | 0 | 3
Script Generator | 0 | 0 | 0 | 0 | 24
Integration Tests and Documentaions | 0 | 0 | 0 | 0 | 5
Scraper | 0 | 0 | 0 | 0 | 5
System Testing and Documentation | 0 | 0 | 0 | 0 | 5
Release Document | 0 | 0 | 0 | 0 | 3
Effort Estimated | 29 | 27 | 29 | 13 | 98
Actual Effort | 8.5 | 0 | 0 | 0 | 8.5